## Version History
;
Project Information
| Project: | Retail Management System
| Client: | TESCO
Start Date:
Team:
| Date | Description | Version | Author | Reviewer
| 2015-09-15 | Initial Version | 1 | Krishna Kumar S

## Product Backlog
Global Edify Auto Insurance Claim Project
Product Backlog
User Story Id | Module | Feature | User Stories | Priority | Sprint Details | Status
USID1 | User(Sonu) |  | As a customer I should be able to claim my policy.
USID2 | User |  | As a Customer I should have timeLine .
USID3 | User
USID4 | User |  | As a registered customer I should be able to view my old claims.
USID5 | User
USID6 | User
USID7 | Global Edify Officer |  | As a Global Edify Officer, I should be able to get notified when a claim is raised.
USID8 | Global Edify Officer |  | As a Global Edify Officer, I should be able to download or view all relavent documents of a claim
USID9 | Global Edify Officer |  | As a Global Edify Officer, I should be allowed to comment on the claim raised.
USID10 | Global Edify Officer |  | As a Global Edify Officer, I should be allowed to view the claim history.
USID11 | Global Edify Officer |  | As a Global Edify Officer, I should be allowed to accept or reject the claim.
USID12 | Claim Officer(Manisha) |  | As a Claim Officer,I should be able to search the assessors according to region.
USID13 | Claim Officer |  | As a Claim Officer,I should be able to assign claims to assessor based on region.
USID14 | Claim Officer |  | As a Claim Officer,I should be allowed to view report sent by assessor.
USID15 | Claim Officer |  | As a Claim Officer,I should forward claim details to claim authorizer.
USID16 | Claim Officer |  | As a Claim Officer,I should be allowed to reject the claim.
USID17 | Assessor(Likitha) |  | As an Assessor, I should be able to view and search the records.
USID18 | Assessor |  | As an Assessor, I should be able to print selected records.
USID19 | Assessor |  | As an Assessor, I should shedule a meeting with the customer by sending SMS.
USID20 | Assessor |  | As an Assessor, I should be able to navigate to the custemer's address.
USID21 | Assessor |  | As an Assessor, I should be able to verify and submit the reports online.
USID22 | Claim Authorizer(Hasitha) |  | As a Claim Authorizer,I want complete customer details, because it is me,who have to negotiate with the customer directly.
USID23 | Claim Authorizer |  | As a Claim Authorizer,I want the track of all the processes after the insurance has been approved because we need to update these information to the customer.
USID24 | Claim Authorizer |  | As a Claim Authorizer,I want the insurance officer to acknowledge me about the rejection of the policy.
USID25 | Claim Authorizer |  | As a Claim Authorizer,I want to know all the details about the amount of money released for material damages and the diagnosis because I need to convince the customer regarding the amount released.
USID26
USID27
USID28
USID29
USID30
USID31
USID32
USID33
USID34
USID35
USID36
USID37
USID38
USID39
USID40
USID41
USID42
USID43
USID44
USID45
USID46
USID47
USID48
USID49
USID50
USID51
USID52
USID53
USID54
USID55
USID56
USID57
USID58
USID59
USID60
USID61
USID62
USID63
USID64
USID65
USID66
USID67
USID68
USID69 |  |  |  | 1
USID70 |  |  |  | 1
USID71 |  |  |  | 1
USID72 |  |  |  | 1
USID73 |  |  |  | 1
USID74 |  |  |  | 1
USID75 |  |  |  | 1
USID76 |  |  |  | 1
USID77 |  |  |  | 1
USID78 |  |  |  | 1
USID79 |  |  |  | 1
USID80 |  |  |  | 1

## Sprint TimeLines
Project Timelines
Sprint No | Title | Start Date | End Date | Weeks | Days | Effort - Hrs | Release Date | Review Date | Retrosp Date | Success Criteria | Remarks/Comments
1 | As a customer I should be able to claim my policy. | 2016-08-16 | 2016-10-01 | 0 | 4 | 10 | 2016-10-01
2 | As a Customer I should have timeLine . | 2016-08-16 | 2016-10-01 | 0 | 4 | 10 | 2016-10-01
3 |  | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
4 | As a registered customer I should be able to view my old claims. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
5 | As a customer I would register for a new policy. | 2016-08-16 | 2016-10-01 | 0 | 4 | 12 | 2016-10-01
6 |  | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
7 | As a Global Edify Officer, I should be able to get notified when a claim is raised. | 2016-08-16 | 2016-10-01 | 0 | 4 | 15 | 2016-10-01
8 | As a Global Edify Officer, I should be able to download or view all relavent documents of a claim | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
9 | As a Global Edify Officer, I should be allowed to comment on the claim raised. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
10 | As a Global Edify Officer, I should be allowed to view the claim history. | 2016-08-16 | 2016-10-01 | 0 | 4 | 15 | 2016-10-01
11 | As a Global Edify Officer, I should be allowed to accept or reject the claim. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
12 | As a Claim Officer,I should be able to search the assessors according to region. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
13 | As a Claim Officer,I should be able to assign claims to assessor based on region. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
14 | As a Claim Officer,I should be allowed to view report sent by assessor. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
15 | As a Claim Officer,I should forward claim details to claim authorizer. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
16 | As a Claim Officer,I should be allowed to reject the claim. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
17 | As an Assessor, I should be able to view and search the records. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
18 | As an Assessor, I should be able to print selected records. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
19 | As an Assessor, I should shedule a meeting with the customer by sending SMS. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
20 | As an Assessor, I should be able to navigate to the custemer's address. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
21 | As an Assessor, I should be able to verify and submit the reports online. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
22 | As a Claim Authorizer, I want a notification page to get notifications from others. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
23 | As a Claim Authorizer,I want the history of all the claims made by the respective claim authoriser | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
24 | As a Claim Authorizer,I want google maps to fix the location. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
25 | As a Claim Authorizer,I want to block the date in the Calender to meet the customer for the negotiation. | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
26 | As a Claim Authoriser, i want timeline to know the complete policy information | 2016-08-16 | 2016-10-01 | 0 | 4 |  | 2016-10-01
27

## Sprint 1 - Plan
Sprint 1 - Plan
Days | Date | Day | 9.00 - 10.00 | 10.00-11.00 | 11.00-12.00 | 12.00-1.00 | 1.00-2.00 | 2.00-3.00 | 3.00-4.00 | 4.00 - 5.00 | 5.00 - 6.00
1 | 2015-10-01 | Thur
| 2015-10-02 | Fri
| 2015-10-03 | Sat
| 2015-10-04 | Sun
2 | 2015-10-05 | Mon
3 | 2015-10-06 | Tue
4 | 2015-10-07 | Wed
5 | 2015-10-08 | Thu
6 | 2015-10-09 | Fri
7 | 2015-10-10 | Sat
| 2015-10-11 | Sun
8 | 2015-10-12 | Mon
9 | 2015-10-13 | Tue
10 | 2015-10-14 | Wed
11 | 2015-10-15 | Thu
12 | 2015-10-16 | Fri
13 | 2015-10-17 | Sat
| 2015-10-18 | Sun
14 | 2015-10-19 | Mon | Integration | Release - 1 |  | Retrospection Meeting | Lunch | Testing and Bug Fixing
15 | 2015-10-20 | Tue | Testing and Bug Fixing |  |  |  | Lunch | Integration | Final Release |  | Smoke Testing
16 | 2015-10-21 | Wed | Presentation Preparation |  |  |  | Lunch | Presentation Review | Project Presentation

## Sprint 1 - Effort Estimate
Sprint 1 Effort Estimate
No Of Stories |  | Level - Hours Distribution |  | Hours Available Per Person |  |  | 70 | 2 | Effort Summary
Level. | Count. | Level. | Total Hrs | Days | Date | Day | Hours Avail | Hours Spt | Hours Available
Simple | 2 | Simple | 223 | 1 | 2015-10-01 | Thur | 2 | 2 | Hours Available Per Person | 70
Medium | 2 | Medium | 0 |  | 2015-10-02 | Fri |  |  | Number of People | 15
Complex | 3 | Complex | 0 |  | 2015-10-03 | Sat |  |  | Total Hours Available | 1050
Grand Total | 7 | Grand Total | 223 |  | 2015-10-04 | Sun
|  |  |  | 2 | 2015-10-05 | Mon | 2 | 0 | Hours Needed | 223
|  |  |  | 3 | 2015-10-06 | Tue | 2 | 0
|  |  |  | 4 | 2015-10-07 | Wed | 2 | 0 | Final Total | -827
|  |  |  | 5 | 2015-10-08 | Thu | 2 | 0
|  |  |  | 6 | 2015-10-09 | Fri | 2 | 0
|  |  |  | 7 | 2015-10-10 | Sat | 2 | 0
[5 empty] | 2015-10-11 | Sun
|  |  |  | 8 | 2015-10-12 | Mon | 4 | 0
|  |  |  | 9 | 2015-10-13 | Tue | 4 | 0
|  |  |  | 10 | 2015-10-14 | Wed | 4 | 0
|  |  |  | 11 | 2015-10-15 | Thu | 4 | 0
|  |  |  | 12 | 2015-10-16 | Fri | 8 | 0
|  |  |  | 13 | 2015-10-17 | Sat | 8 | 0
[5 empty] | 2015-10-18 | Sun
|  |  |  | 14 | 2015-10-19 | Mon | 8 | 0
|  |  |  | 15 | 2015-10-20 | Tue | 8 | 0
|  |  |  | 16 | 2015-10-21 | Wed | 8 | 0
Formulas:
Date = [Date, row above]+1

## Sprint 1 - Effort Est Details
Sprint 1 -Estimate
Sl No | Story | Assigned To | Level | UX | UI | Design | Code | Unit Testing | Self Review | Integration | Testing | Total in hrs
1 |  |  | Simple | 30 | 32 | 23 | 30 | 20 | 22 | 12 | 20 | 3.15
2 |  |  | Simple | [8 empty] | 0
3 |  |  | Medium | [8 empty] | 0
4 |  |  | Medium | [8 empty] | 0
5 |  |  | Complex | [8 empty] | 0
6 |  |  | Complex | [8 empty] | 0
7 |  |  | Complex | [8 empty] | 0
8 | [11 empty] | 0
9 | [11 empty] | 0
10 | [11 empty] | 0
11 | [11 empty] | 0
12 | [11 empty] | 0
13 | [11 empty] | 0
14 | [11 empty] | 0
15 | [11 empty] | 0
16 | [11 empty] | 0
17 | [11 empty] | 0
18 | [11 empty] | 0
19 | [11 empty] | 0
20 | [11 empty] | 0
21 | [11 empty] | 0
22 | [11 empty] | 0
23 | [11 empty] | 0
24 | [11 empty] | 0
25 | [11 empty] | 0
26 | [11 empty] | 0
27 | [11 empty] | 0
28 | [11 empty] | 0
29 | [11 empty] | 0
30 | [11 empty] | 0
31 | [11 empty] | 0
32 | [11 empty] | 0
33 | [11 empty] | 0
34 | [11 empty] | 0
35 | [11 empty] | 0
36 | [11 empty] | 0
37 | [11 empty] | 0
38 | [11 empty] | 0
39 | [11 empty] | 0
40 | [11 empty] | 0
41 | [11 empty] | 0
42 | [11 empty] | 0
43 | [11 empty] | 0
44 | [11 empty] | 0
45 | [11 empty] | 0
46 | [11 empty] | 0
47 | [11 empty] | 0
48 | [11 empty] | 0
49 | [11 empty] | 0
50 | [11 empty] | 0

## Sprint 1 Backlog
Sprint BackLog - Sprint 1
Task Id | UserStory ID | Tasks | Person | Estimated (Hrs) | Status
T1
T2
T3
T4
T5
T6
T7
T8
T9
T10
T11
T12
T13
T14
T15
T16
T17
T18
T19
T20
T21
T22
T23
T24
T25
T26
T27
T28
T29
T30
T31
T32
T33
T34
T35
T36
T37
T38
T39
T40
T41
T42
T43
T44
T45
T46
T47
T48
T49
T50
T51
T52
T53
T54
T55
T56
T57
T58
T59
T60
T61
T62
T63
T64
T65
T66
T67
T68
T69
T70
T71
T72
T61
T62
T63
T64
T65
T66
T67
T68
T69
T70
T71
T72
T61
T62
T63
T64
T65
T66
T67
T68
T69
T70
T71
T72

## People
Team
SL. No | Name | Role | E - Mail ID | Contact #
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21

## Miscalleneous
Project Repository Details |  |  | Configuration Details
SL. No | Name | Location | SL. No | Name | Branch | Location
1 |  |  | 1
2 |  |  | 2
3 |  |  | 3
4 |  |  | 4
5 |  |  | 5
Hardware Checklist
|  |  | SL. No | Name | Category | Remarks
1
2
3
4
5

## Legends
Status | Level
Open | Simple
Pending | Medium
Closed | Complex